## Slide 1: Group 2 Project Update: Week 6
Paul Kruchko-Project Manager
Mike Laba-ME Design Lead
Bryan Jagielo-EE Design Lead

## Slide 2: ME Design Status
Simulation: Correct motion with 5 fasteners
Initiated FEA for dispense box
4 of 6 actuator plates finished
Machine frame design complete
Initiated mounting considerations of electrical components and motor
Constant for return springs of slide-dispense mechanism determined to between 60.75 and 187.5 N/m

## Slide 3: ME Design TODO
Full motion simulation study with 50 pieces of every type of fastener to be dispensed (6 simulations for 6 fastener types)
  Who: Mike
  When: Complete by Sunday, 12 Oct.
Finish FEA of dispense box & slide mechanism
  Who: Mike
  When: Complete by Sunday, 19 Oct.
Exact P/Ns and quantity needed for 80/20 machine frame hardware given to Project Manager
  Who: Mike & Audrey
  When: Complete by Sunday, 12 Oct.

## Slide 4: ME Design TODO, cont’d
Total baseline volume of ABS material needed
  Who: Mike & Audrey
  When: Complete by Sunday,12 Oct.
More accurate mass moment of inertia for load
  Who: Steven
  When: Complete by Sunday, 12 Oct
Finish last two actuator plates
  Who: Audrey
  When: Complete by Thursday, 9 Oct
Complete HMI panel design
  Who:

## Slide 5: EE Design Status
Preliminary Sensor design complete
Microcontroller purchased, ready for prototyping
Preliminary code structure complete: State machine

## Slide 6: EE Design TODO
Finalize motor selection
  The current motor selection was scrapped in favor of a vendor that was able to give a more complete datasheet with motor specifications and coefficients needed for accurate system model: Pittman.
  Motor is still comparable to previous selection in regards to torque, speed, and encoder availability
    Who: Paul
    When: Complete by 11 Oct

## Slide 7: EE Design TODO, cont’d
Finalize system model with coefficients and perform MATLAB/Simulink simulations for frequency response, step response, impulse response.
  Who: Paul & Bryan
  When: Complete by 12 Oct.
Finalize motor selection with mechanical mounting specifications for ME team
  Who: Paul
  When: Complete by 11 Oct
Finish Design and Prototype Sensor circuit, present mechanical mounting specifications to ME design team
  Who: Terry & Monika
  When: Complete by Sunday, 12 Oct

## Slide 8: EE Design TODO, cont’d
Selection of push buttons and LCD with prototyping
  Who: Monika and Terry
  When: Complete by 19 Oct
Design and Prototype power supply circuit
  Who: Paul
  When: Complete by 25 Oct
Design digital motor controller to be implemented in code
  Who: Paul and Bryan
  When: Complete by 25 Oct

## Slide 9: Project Status Summary
System development is on schedule. End design phase target is still 25 October
Initial motion simulations are promising and verify the major function of the gravity assisted design
Final BOM and purchasing of components and material also on target for 25 October.